## Sheet1
Risk Register
Risk ID | Risk Statement |  |  | Risk Response | Risk Description | Risk Owner | Probability % | Impact | Risk Rating | Risk Type | Category | Trigger | Contigency Plan | Contigency Owner | Comments
| Cause | Event | Effect
1 | As a result of power outage from the primary source of electrical supply | there may be a disruption in the use of machinery and equipment. | which may delay the workers from completing the assigned task thereby negatively impacting the schedule. | Mitigate | This risk will be reduced by ensuring the secondary power supply ( Solar Panel and Backup Generators) are properly connected to the power control board to provide electricity when primary electric supply fails. | Shubham | 80% | Moderate-3 (Estimated Duration 5 Days) | High-4 | Threat | Technical (Process) | If there is a power outage in the areas 2 km away from the construction site. | If a power outage occurs the solar panel node on the power control board should be switched on immediately. | Electrician
2 | Due to the continuous instability of political affairs in Nigeria, | there might be a rise in inflation , | which may lead to a higher price of materials thereby negatively impacting the project budget by increasing the cost. | Mitigate | This risk will be mitigated by sigining a Fixed Price Contract with the procurement vendors in order to prevent a change in the price that is previously estimated. | Infant | 70% | Very High-5 (Estimated Cost > 56250) | High-4 | Threat | Internal (Procurement) | If the Consumer Price Index (CPI) increases by more than 5 % over a 6 months period and nigerian government fiscal deficit exceed 3 % of GDP. | If inflation occurs and the vendors are refusing to comply with the fixed-price contract, we will be re-negotiating the fixed-price contract by setting cost caps( Maximum 5% increase in prices). | Project Manager
3 | As a result of Nigerian government officials going on strike due to dispute. | the land officials might be absent from office. | This may result in the delay of Project land permit approval which will adversely impact the project schedule. | Accept | This risk will be accepted as it is above our control. | Oluwasomidotun | 20% | Low-2 (Estimated Duration -3 days) | Low-2 | Threat | External (Permits) | If government officials publish news about going on strike in < 5 days. | No Contingency plan would be made because it is out of our jurisdiction. | N/A
4 | Due to the storage of construction materials at the site location | local residents in the community may steal the materials | This may lead to a shortage of materials and additional purchase has to be made, which will increase the project budget. | Mitigate | This risk will be mitigated by applying the just-in-time (JIT) Practice, whereby the contractor delivers only the needed material and supplies for the ongoing construction phase. | Veraline | 80% | Very High-5 (Estimated Cost > 56250) | Very High-5 | Threat | External (theft) | If there are more than 3 reported incidences of unauthorized access by unknown people at the construction site in a week. | Install CCTV cameras around the construction site and motion-sensitive lighting at the entry point of where construction materials are located or kept. | Electrician
5 | As a result of untimely payment of workers wages | the workers might conduct a protest | This may result in a stoppage of work, which will cause a delay in the project schedule. | Mitigate | This risk will be reduced by implementing a worker's pay sheet linked to a calendar reminder which is automatically set before the due date to ensure timely payments. | Sakshi | 70% | Moderate - 3 (Estimated time- 7 days) | Medium-3 | Threat | Internal (Employees) | If more than 15% of workers raised formal complaints regarding late payments of Salaries in a month. | Implement a backup digital payroll system, which will be used to ensure workers are paid in a timely manner when the calendar system fails. | Project Manager
6 | As a result of Signal disruptions in the northern rural area ( Borno) | this may cause most of the important information of the project not to be televised | Leading to mismanagement of resources as the community members are not being informed thereby negatively impacting the budget of the project. | Avoid | This risk will be avoided by not proceeding with national television publication by changing the scope to publication on social network television. | Shubham | 80% | High-4 (Estimated time- 10 days) | Very High-5 | Threat | Technical (Technology) | If there is a disruption in signal within 3 km of the community . | Create offline communication channels via newsletter and collaborate with local radio stations to provide information regarding the project's progress. | Marketing Specialist
7 | As a result of grammatical errors on the waterplant manuals | This may result in the need to reprint all waterplant manuals | Which will lead to higher cost in reprinting, thereby increasing the project budget. | Avoid | This risk would be avoided by not printing the waterplant manual and changing the scope to having only soft copies of the waterplant report to accommodate any needed changes and not incure additional cost. | Infant | 70% | High-4 (Estimated time- 10 days) | High-4 | Threat | Internal (Employees) | if more than 10 errors are found in the entire manual. | Create a secondary method of providing the water plant manual via providing soft copies to the workers to ensure that the information provided is correct and thus not contain any misleading information. | Project Manager
8 | Due to the high rate of insurgency in the northern region of Nigeria(Borno) | This may result in the hijack of the waterplant project by the insurgent group and the construction area sealed off | This will lead to the stop of the project work which will negatively impact the project schedule. | Transfer | This risk would be transferred to the Nigerian Military Forces and Government so they can tackle the situation. | Oluwasomidotun | 50% | High-4 (Estimated time- 10 days) | High-4 | Threat | External (Terrorism) | if more than 2 news channels display news of a high rate of insurgency in the northern region of Nigeria | the risk is transferred to the Nigerian military and government. Hence, they are liable for the further actions to be taken. | Nigerian Military forces and government
9 | Due to bad roads in Borno state. | There may be a chance that the transportation vehicle conveying the materials might be involved in an accident | This wil result in the damage of the materials, leading to the re-purchase thereby negatively impacting the project budget. | Transfer | This risk will be transferred to the project assigned insurance company and the logistics company. By having a contract agreement with insurance brokers and selected transportation company prior to the start of the project. | Veraline | 80% | Very High-5 (Estimated cost- > $ 56,250) | Very High-5 | Threat | External (Environmental and Transportation) | if more than 2 km of the road appears to be muddy and slushy instead of tar roads may cause a accidents. | the risk is transferred to the Insurance and Logistics Company. Hence, they are liable for the further actions to be taken. | Project Manager, Insurance company, Logistics company, and Logistics coordinator.
10 | As a result of drought happening in Africa. | There might be a limited supply of raw water from the approved second source which is River Ngadda. | This will result in a reduced scope as the quantity of purified water might be lower than the stated amount on the project objective. | Accept | This risk will be accepted because it is out of our control as it is an environmental crisis | Sakshi | 20% | Very High-5 | Medium-3 | Threat | External (Environmental) | if more than 3 countries of Africa face drought then there are chances of drought in Nigeria as well. | No Contingency plan would be made because it is out of our jurisdiction. | N/A
Borno Ruwa Project Impact Table |  |  |  | MGMT8370 HEAT MAP – Borno Ruwa Project
Impact Rating | Cost | Time (Days) |  | Threats | [6 empty] | Opportunities
-1- | < $ 18,750 | < 3 |  |  | 91% - 99% | - 4 - | - 4 - | - 5 - | - 5 - | - 5 - | - 5 - | - 5 - | - 5 - | - 4 - | - 4 - | 91% - 99%
Very Low |  |  |  | Probability | Very High | High | High | Very High | Very High | Very High | Very High | Very High | Very High | High | High | Very High | Probability
-2- | $18,750 - $ 30,000 | 3-4 | [6 empty] | - 5 - | - 5 - | - 5 - | - 5 -
Low |  |  |  |  | 76% - 90% | - 3 - | - 4 - | - 4 - | Very High | Very High | Very High | Very High | - 4 - | - 4 - | - 3 - | 76% - 90%
-3- | $ 30,001- $46,000 | 5-9 |  |  | High | Med | High | High |  |  |  |  | High | High | Med | High
Moderate
-4- | $ 46,001- $ 56,250 | 10-15 |  |  | 26% - 75% | - 3 - | - 3 - | - 3 - | - 4 - | - 4 - | - 4 - | - 4 - | - 3 - | - 3 - | - 3 - | 26% - 75%
High |  |  |  |  | Medium | Med | Med | Med | High | High | High | High | Med | Med | Med | Medium
-5- | > $56,250 | > 15 |  |  |  | - 1 - | [8 empty] | - 1 -
Very High |  |  |  |  | 6% - 25% | Very Low | - 2 - | - 2 - | - 3 - | - 3 - | - 3 - | - 3 - | - 2 - | - 2 - | Very Low | 6% - 25%
[5 empty] | Low |  | Low | Low | Med | Med | Med | Med | Low | Low |  | Low
[6 empty] | - 1 - | - 1 - | - 1 - |  |  |  |  | - 1 - | - 1 - | - 1 -
Risk Reserve | 15 % of 2.50 Miliion | 375000 |  |  | 1% - 5% | Very Low | Very Low | Very Low | - 2 - | - 2 - | - 2 - | - 2 - | Very Low | Very Low | Very Low | 1% - 5%
[5 empty] | Very Low |  |  |  | Low | Low | Low | Low |  |  |  | Very Low
[6 empty] | - 1 - |  |  |  | - 5 - | - 5 - |  |  |  | - 1 -
[6 empty] | Very Low | - 2 - | - 3 - | - 4 - | Very High | Very High | - 4 - | - 3 - | - 2 - | Very Low
[7 empty] | Low | Med | High |  |  | High | Med | Low
Impact
References
Lisa Pollard. (n.d).Week 4 Risk Identification [PowerPoint slides]. eConestoga. https://conestoga.desire2learn.com/d2l/le/content/1253758/viewContent/26353301/View
Lisa Pollard. (n.d).Week 10 Overall Risk Management [PowerPoint slides]. eConestoga. https://conestoga.desire2learn.com/d2l/le/content/1253758/viewContent/26353359/View
Lisa Pollard. (n.d).Week 5 Quantitative Analysis [PowerPoint slides]. eConestoga. https://conestoga.desire2learn.com/d2l/le/content/1253758/viewContent/26353359/View
Lisa Pollard. (n.d).Week 9 Risk Response Planning [PowerPoint slides]. eConestoga. https://conestoga.desire2learn.com/d2l/le/content/1253758/viewContent/26353357/View
Lisa Pollard. (n.d). Week 11 Contigency Plans [PowerPoint slides]. eConestoga. https://conestoga.desire2learn.com/d2l/le/content/1253758/viewContent/26353358/View
Conestoga College. (n.d). Assignment 3 Template [PDF]. eConestoga.https://conestoga.desire2learn.com/d2l/le/content/1253758/viewContent/27850444/View

## Sheet2
Borno Ruwa Project Impact Table |  |  | MGMT8370 HEAT MAP – Borno Ruwa Project
Impact Rating | Cost | Time (Days) | Threats | [6 empty] | Opportunities
-1- | < $ 18,750 | < 3 |  | 91% - 99% | - 4 - | - 4 - | - 5 - | - 5 - | - 5 - | - 5 - | - 5 - | - 5 - | - 4 - | - 4 - | 91% - 99%
Very Low |  |  | Probability | Very High | High | High | Very High | Very High | Very High | Very High | Very High | Very High | High | High | Very High | Probability
-2- | $18,750 - $ 30,000 | 3-4 | [5 empty] | - 5 - | - 5 - | - 5 - | - 5 -
Low |  |  |  | 76% - 90% | - 3 - | - 4 - | - 4 - | Very High | Very High | Very High | Very High | - 4 - | - 4 - | - 3 - | 76% - 90%
-3- | $ 30,001- $46,000 | 5-9 |  | High | Med | High | High |  |  |  |  | High | High | Med | High
Moderate
-4- | $ 46,001- $ 56,250 | 10-15 |  | 26% - 75% | - 3 - | - 3 - | - 3 - | - 4 - | - 4 - | - 4 - | - 4 - | - 3 - | - 3 - | - 3 - | 26% - 75%
High |  |  |  | Medium | Med | Med | Med | High | High | High | High | Med | Med | Med | Medium
-5- | > $56,250 | > 15 |  |  | - 1 - | [8 empty] | - 1 -
Very High |  |  |  | 6% - 25% | Very Low | - 2 - | - 2 - | - 3 - | - 3 - | - 3 - | - 3 - | - 2 - | - 2 - | Very Low | 6% - 25%
|  |  |  | Low |  | Low | Low | Med | Med | Med | Med | Low | Low |  | Low
[5 empty] | - 1 - | - 1 - | - 1 - |  |  |  |  | - 1 - | - 1 - | - 1 -
Risk Reserve | 15 % of 2.50 Miliion | 375000 |  | 1% - 5% | Very Low | Very Low | Very Low | - 2 - | - 2 - | - 2 - | - 2 - | Very Low | Very Low | Very Low | 1% - 5%
|  |  |  | Very Low |  |  |  | Low | Low | Low | Low |  |  |  | Very Low
[5 empty] | - 1 - |  |  |  | - 5 - | - 5 - |  |  |  | - 1 -
[5 empty] | Very Low | - 2 - | - 3 - | - 4 - | Very High | Very High | - 4 - | - 3 - | - 2 - | Very Low
[6 empty] | Low | Med | High |  |  | High | Med | Low
Impact